## Week 13
Daily Stand-up Meeting Report
Week: December 04 - December 10
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on the reuirements document | 1) Worked on the reuirements document
| 2) Work on the requirements | 2) Work on the requirements
| 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1)Worked on the end-term artifacts. | 1)Worked on the end-term documents
| 2)Working on the end-term documents | 2)Working on the end-term documents.
| 3)No obstacles till now. | 3)No obstacles till now.
Rupanandha | 1)Worked on the requirements document changes. | 1)Worked on the end-term documents
| 2)Working on the preparing ppt. | 2)Working on the end-term documents.
| 3)No blockers | 3)No blockers.
Mani | 1)Worked on the end-term artifacts. | 1)Worked on the end-term artifacts.
| 2)Working on the end-term documents | 2)Working on the end-term documents
| 3)No Major obstacles | 3)No Major obstacles
vamsy | 1)Made some changes to the requirements document. | 1)Made some changes to the requirements document.
| 2)Working on the requirements document. | 2)Finalized the Changes to the end term documents.
| 3)No Major obstacles | 3)No Major obstacles
Teja | 1) Reviewed all the changes made to the requirements document. | 1) Reviewed all the changes made to requirements document.
| 2) Made some changes while skimming through the document. | 2) Discussed with my team regarding the changes.
| 3) No major challenges. | 3) No major challenges.
Ram Naveen | 1. Worked on project management plan. | 1. Checking on documents which we have to submit.
| 2. Scrutinizing entire documents for the project. | 2. Have to submit the documents to the client.
| 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 12
Daily Stand-up Meeting Report
Week: November 27 - December 03
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Updated new requirements | 1) Updated new requirements | 1) Updated new requirements | 1) Updated new requirements | 1) Updated new requirements
| 2) Understanding new requirments | 2) Understanding new requirments | 2) Understanding new requirments | 2) Understanding new requirments | 2) Understanding new requirments
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents.
| 2)Modifing the documents as per the suggestions. | 2)Updating the documents as per the suggestions. | 2)Modifing the documents as per the suggestions. | 2)Updating the documents as per the suggestions. | 2)Modifing the documents as per the suggestions.
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Rupanandha | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents. | 1) Worked on the modifications of the documents.
| 2)Modifing the documents as per the suggestions. | 2)Updating the documents as per the suggestions. | 2)Modifing the documents as per the suggestions. | 2)Updating the documents as per the suggestions. | 2)Modifing the documents as per the suggestions.
| No Blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1)made some changes to Issues documents. | 1)made some changes to Issues documents. | 1)made some changes to Issues documents. | 1)made some changes to Issues documents. | 1)made some changes to Issues documents.
| 2) Started modifying the documents. | 2) Started modifying the documents. | 2) Started modifying the documents. | 2) Started modifying the documents. | 2) Started modifying the documents.
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
vamsy | 1)made some changes to Issues documents. | 1)Finalized the changes to the issues Document. | 1)Worked with the team regarding changes to be made in Requirements Documents. | 1)Worked with the team regarding changes to be made in Requirements Documents. | 1)Had a team meeting.
| 2)Finalize the changes to the issues Document | 2)Working with the team regarding changes to be made in Requirements Documents. | 2)Working with the team regarding changes to be made in Requirements Documents. | 2)Team Meeting | 2)Should make some changes to the requirements documents based on the team meeting.
| 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles
Teja | 1) Worked on the modifications that were to be made. | 1) Continued modifying the documents. | 1) Worked on the document modification. | 1) Worked on the document with my team. | 1) Discussed about the final presentation with my team.
| 2) Started modifying the documents. | 2) Started updating the documents with the changes. | 2) Modified document as per requirements. | 2) Discussed modifications with my team. | 2) Updated the discussed changes in the documents.
| 3) No major obstacles | 3) No major obstacles. | 3) No major challenges. | 3) No major obstacles. | 3) No major obstacles.
Ram Naveen | 1. Got the changes from the client. | 1. Prepared more precise test cases. | 1. Test suit has been updated | 1. Submitted test suit to the team members. | 1. Completed prototypes with the clear view.
| 2. Working on comments made by the client. | 2. Done the test suit accordingly. | 2. Submitted to the team members. | 2. Done some modifications in the prototypes. | 2. Working on some part of project management plan.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 11
Daily Stand-up Meeting Report
Week: November 13 - November 19
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on Project management plan | 1) Worked on Project management plan | 1) Worked on Project management plan | 1) Worked on Project management plan | 1) Worked on Project management plan
| 2) Working on PM Plan | 2) Working on PM Plan | 2) Working on PM Plan | 2) Working on PM Plan | 2) Working on PM Plan
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1)Worked on the end-term documentation. | 1)Worked on the end-term presentation document. | 1)Worked on the end -term presentation. | 1)Got some idea with the latest requirements. | 1)Got some idea with the latest requirements.
| 2)Working on the end-term presentation. | 2)Working on the end-term documents. | 2)Getting idea with the latest requirements | 2)Checking the new requirements and learning from it. | 2)Working on the issues.
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Rupanandha | 1)Worked on the end-term documentation. | 1)Worked on the end-term presentation document. | 1)Worked on the end -term presentation. | 1)Got some idea with the latest requirements. | 1)Got some idea with the latest requirements.
| 2)Working on the end-term presentation. | 2)Working on the end-term documents. | 2)Getting idea with the latest requirements | 2)Checking the new requirements and learning from it. | 2)Working on the issues.
| 3)No Blockers | 3)No Blockers | 3)No Blockers | 3)No Blockers | 3)No Blockers
Mani | 1)Worked on the end-term documentation. | 1)Worked on the end-term documentation. | 1. Made some canges regarding test cases. | 1. Made some canges regarding test cases. | 1. Made some canges regarding test cases.
| 2. Continued working on test cases | 2. Continued working on test cases | 2. Continued working on test cases | 2) Continued working on the documents | 2) Continued working on the documents
| 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles
vamsy | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents. | 1) End-term presentation. | 1)Made some changes to documents
| 2) Working on the end-term presentation documents. | 2) Working on the end-term presentation documents. | 2)End term presentation | 2)Should make some changes to documents. | 2)Should make some changes to documents.
| 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles | 3)No Major obstacles
Teja | 1) Worked on the documents required for the end-term presentation. | 1) Worked on the documents required for the end term presentation. | 1) Worked on the end term presentation documents. | 1) End term presentation. | 1) Have made some modifications to the documents.
| 2) Continued working on the documents | 2) Continued working on the documents. | 2) End term presentation. | 2) Slight modifications need to be made in the document. | 2) Should make some slight modifications to the documents.
| 3) No major obstacles | 3) No major obstacles. | 3) No major obstacles. | 3) No major obstacles | 3) No major obstacles.
Ram Naveen | 1. Done test cases for the end term presentation. | 1. Worked on test cases. | 1. Made some canges regarding test cases. | 1. Given presentation on the project | 1. End term presentation for our group
| 2. Continued working on test cases | 2. Submitted with the team. | 2, Given End term presentation | 2. Waiting comments from the client. | 2. Had prsented well among the team.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 10
Daily Stand-up Meeting Report
Week: November 6 - November 12
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Document new requirements | Document new requirements | Document new requirements | Document new requirements | Document new requirements
| Discuss with client | Discuss with team members | Team meeting | Team meeting | Team meeting
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1)Worked on end term presentation documentation. | 1)Worked on end term presentation documentation. | 1)Worked on end term presentation documentation. | 1)Worked on end term presentation documentation. | 1)Worked on end term presentation documentation.
| 2)Discussing with team and completing the end term presentation documentation. | 2)Discussing with team and completing the end term presentation documentation. | 2)Discussing with team and completing the end term presentation documentation. | 2)Discussing with team and completing the end term presentation documentation. | 2)Discussing with team and completing the end term presentation documentation.
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Rupanandha | 1.Working on end term presentation documentation | 1.Working on end term presentation documentation | 1.Working on end term presentation documentation | 1.Working on end term presentation documentation | 1.Working on end term presentation documentation
| 2.Discussed with team about the work progress | 2.Discussed with team about the work progress | 2.Discussed with team about the work progress | 2.Discussed with team about the work progress | 2.Discussed with team about the work progress
| 3.No issues | 3.No issues | 3.No issues | 3.No issues | 3.No issues
Mani | 1)worked on Project management plan | 1)completed 25% of end term ppt. | 1)Completed 50 % of end term ppt. | 1)Completed 75 % of end term ppt. | 1)Completed 100 % of end term ppt.
| 2)should work on project end term presentation. | 2)should complete 50% of end ppt. | 2)should complete 75% of end ppt. | 2)should complete 100% of end ppt. | 2)Should prepare for giving the presentation.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents. | 1) Worked on the end-term presentation documents.
| 2) Working on the end-term presentation documents. | 2) Working on the end-term presentation documents. | 2) Working on the end-term presentation documents. | 2) Working on the end-term presentation documents. | 2) Working on the end-term presentation documents.
| 3)No Obstacles. | 3)No Obstacles. | 3)No Obstacles. | 3)No Obstacles. | 3)No Obstacles.
Teja | 1)Worked on documents that are required for end-term presentation | 1) Fetched the data required to make the documents | 1) Attended team meetings and gathered information required to make the documents | 1) Worked on documents that are required for end term presentation | 1) Worked on documents that are required for end term presentation
| 2) Worked on the end term presentation documents | 2) Work on the end term presentation documents | 2) Continued Working on the documents | 2) Worked on the end term presenation documents | 2) Continued working on the documents
| 3) No major obstacles | 3) No issues till now. | 3) No issues till now. | 3) No issues till now. | No issues till now.
Ram Naveen | 1. Discussed about the end term presentation | 1. Decided my role in the team. | 1. Had a clear vew on test plan | 1. Prepared some more test cases for the project. | 1. Updated more test cases with in the team.
| 2. Divided responsibilities in team. | 2. Discussed on how to do test plan | 2. Wrote some test cases regarding project. | 2. Discussed with the team for new test cases | 2. Documented test cases.
| 3. No issues upto now. | 3. No issues upto now | 3. No issues upto now | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 9
Daily Stand-up Meeting Report
Week: October 30 - November 5
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Gathered some new requirements | Worked on gathered requirements | Gathered some new requirements | Worked on gathered requirements | Gathered some new requirements
| Document them | Document them | Document them | Document them | Document them
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1) Worked on documentation. | 1) Worked on the test documentation 25%. | 1) Worked on the test documentation 50%. | 1) Worked on the test documentation 75%. | 1) Worked on the test documentation 100%.
| 2) Working on the test documentation. | 2) Working on the test documentation. | 2) Working on the test documentation. | 2) Working on the test documentation. | 2) Working on the test documentation.
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1.Working on documentation | 1.Working on documentation | 1.Working on documentation | 1.Working on documentation | 1.Working on documentation
| 2.Working with team on documentaion integration | 2.Working with team on documentaion integration | 2.Working with team on documentaion integration | 2.Working with team on documentaion integration | 2.Working with team on documentaion integration
| 3.No issues | 3.No issues | 3.No issues | 3.No issues | 3.No issues
Mani | 1)worked on Project management plan | 1)worked on Project management plan | 1)worked on Project management plan | 1)Completed 25% of gantt chart. | 1)Complted 50% of gantt chart.
| 2)should work on Project management plan | 2)should work on Project management plan | 2)should work on gantt chart with teja. | 2)should complete 50% work on gantt chert. | 2)worked on Project management plan
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Worked on Documentation. | 1)Worked on Documentation. | 1)Worked on Documentation. | 1)Prepared the Documents. | 1) Updated requiremnets document based on preffor comments.
| 2)Working on Documentation | 2)Working on Documentation | 2)Working on Documentation | 2)Need to have a team meeting inorder to update the Documents. | 2) worked on some more requirements.
| 3)No Issues. | 3)No Issues. | 3)No Issues. | 3)No Issues. | 3)No Issues.
Teja | 1) Worked on documentation | 1) Continued working on documentation | 1) Continued Working on the documentation | 1) Completed the documents to an extent | 1) Continued working on documentation
| 2) Worked on documentation | 2) Worked on documentation | 2) Worked on documentation | 2) Attended team meetings and gained some inputs from the team. | 2) Made some changes to documentation as suggested by the team.
| 3) No issues till now. | 3) No issues till now. | 3) No issues till now. | 3) No issues till now. | No issues till now.
Ram Naveen | 1. Decided to update user documentation | 1. Prepared a user document. | 1. Team has made some changes. | 1. Prepared user documentation. | 1. Updated requiremnets document based on preffor comments.
| 2. Discussed about the user documentation among team. | 2. Shared user document with the team. | 2. Prepared final user documentation. | 2. Had a grop team meeting with to discuss with the update of requirements document. | 2. worked on some more requirements.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 8
Daily Stand-up Meeting Report
Week: October 23 - October 29
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Documenting new requirements | Documenting new requirements | Solved some obstacles | Solvied remaning obstacles | Documenting new requirements
| Documenting new requirements | Documenting new requirements | Solving some obstacles | Solving some obstacles | Documenting new requirements
| 3)No obstacles till now. | 3)No obstacles till now. | Some obstacles | Some obstacles | 3)No obstacles till now.
Ashwini | 1) Worked on the test cases with latest requirements, | 1)Worked on the updated requirements. | 1)Worked on some of requirements. | 1)Worked on the updated requirements. | 1) Worked on the test cases for new requirements.
| 2)Working on the updated requirements | 2)Working on the requirements. | 2)Working on the issues with requirements. | 2)Working on test cases for the new requirements. | 2)Working on test cases for the new requirements.
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1.Discussed with team about the latest requirements updates from cleint. | 1.Discussed with team about the latest requirements updates from cleint. | 1.Discussed with team about the latest requirements updates from cleint. | 1.Discussed with team about the latest requirements updates from cleint. | 1.Discussed with team about the latest requirements updates from cleint.
| 2.Staretd working on documentation | 2.Staretd working on documentation | 2.Staretd working on documentation | 2.Staretd working on documentation | 2.Staretd working on documentation
| 3.No Issues | 3.No Issues | 3.No Issues | 3.No Issues | 3.No Issues
Mani | 1)Started WBS document. | 1)Completed 25% of WBS. | 1)Completed 50% of WBS. | 1)Completed 75% of WBS. | 1)Completed 75% of WBS.
| 2)Should coplete about 25% of WBS with teja. | 2)Should coplete about 50% of WBS with teja. | 2)Should coplete about 75% of WBS with teja. | 2)Should coplete about 100% of WBS with teja. | 2)should start working on gantt chart.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Had Team Meeting. | 1)Added some features to the requirements documents. | 1)Worked on Documentation | 1)Worked on Documentation | 1)Worked on Documentation
| 2)work on Documentation. | 2)Working on documentation. | 2)Working on Documentation | 2)Working on Documentation | 2)Working on Documentation
| 3)No Issues. | 3)No Issues. | 3)No Issues. | 3)No Issues. | 3)No Issues.
Teja | 1) Attended team meeting. | 1) Started working on the wbs document with mani. | 1) Completed 50% of wbs. | 1) Completed 75% of the wbs document, | 1) Completed 75% of wbs.
| 2) Worked on documentation | 2) Continued working on the wbs document. | 2) Started working on the remaining part. | 2) Worked on the wbs document. | 2) Must start working on the gantt chart.
| 3)No major issues | 3) No major issues till now. | 3) No major issues till now. | 3) No major issues till now. | 3) No major issues till now.
Ram Naveen | 1. Read the comments on the requirement document. | 1. Updated the document of the requirements | 1. Made some research on possibility of requirements. | 1. Discussed with the team about them. | 1. Documented those solutions for getting those requirements done.
| 2. Discussed about the latest requrements. | 2. Made some research on possibility of requirements. | 2. Had some douts regarding the requiremnts. | 2. Had some solutions for the requirements. | 2. Had a team meeting with the group.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 7
Daily Stand-up Meeting Report
Week: October 16 - October 22
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Went to client meeting | Solved some problems | Solved some problems | Went to client meeting | Went to client meeting
| Disscuss some problems | Trying to resolve some problems | Trying to resolve some problems | Disscuss some problems | Disscuss some problems
| Some obstacles | Some obstacles | Some obstacles | Some obstacles | Some obstacles
Ashwini | 1)Worked on modifing the documents. | 1) Worked on the requirements. | 1) Worked on the requirements upto 50%. | 1)Worked on the requirements. | 1) Worked in the test cases
| 2)Disscussed some issues with requirements. | 2) Brainstorming the requirements. | 2) Got some idea with requirements | 2) Working in the test cases | 2) Working on the test cases with latest requirements,
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1.Planned a Client meeting to undersatnd the expectation | 1.Took the client appointment | 1.Meet the client | 1.Undersatood the client expectation | 1.Started working on latest updates from cleint
| 2.Inquired about the documenetion progress with team | 2.Inquired about the documenetion progress with team | 2.Inquired about the documenetion progress with team | 2.Inquired about the documenetion progress with team | 2.Inquired about the documenetion progress with team
| 3.No Issues | 3.No Issues | 3.No Issues | 3.No Issues | 3.No Issues
Mani | 1)Finished updating documents. | 1)Discussed about key features of our project. | 1)Discussed some more functionalities of our project. | 1)Partially resolved issues. | 1)Completely resolved issues.
| 2)Need to discuss about key features of our project. | 2)Need to discuss some more functionalities of our project. | 2)Need to resolve the issues. | 2)Should completely resolve the issues. | 2)Need to work on documentation for final presentation.
| 3)No issues till now. | 3)No issues till now. | 3)Some issues regarding functionalities. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Planned a Client meeting to resolve some issues. | 1)Noted down all the issues and took the client appointment. | 1)met the client. | 1)made some changes to prototypes | 1)Updated the Documents
| 2)Note down all the Issues. | 2)Note down all the Issues. | 2)resolved the doubts regarding the requirements document. | 2)Update the documents. | 2)Team meeting
| 3)some issues regarding the Client Requirements. | 3)some issues regarding the Client Requirements. | 3)No issues | 3)No obstacles. | 3)No Obstacles.
Teja | 1) Worked on the test cases of the project. | 1) Worked on the test cases | 1) Had a meeting with the client. | 1) Made some alterations to the test cases according to the client's instructions. | 1) Made the document consisted of all the test cases.
| 2) Considered all the scenarios and noted down all possible test cases for the project. | 2) Continued working on the test cases. | 2) Got clarified with all the doubts we had regarding test cases. | 2) Continued working on the test cases of the project. | 2) Had a discussion with the team and took review of the document from the team.
| 3) No major issues yet. | 3) No major issues till now. | 3)No major issues yet. | 3) No major issues yet. | 3) No major issues yet.
Ram Naveen | 1. Decided to prepare protypes for the project | 1.Build a prototype for the with the additinal requirements. | 1. Copleted prototypes . | 1. Team has made some changes on prototypes | 1. Decided to have meeting among us
| 2. Created some dummy prototypes | 2. Done some research on requiremnts. | 2. presented to the team | 2. Updated prototypes for project. | 2. Had team meeting about the project.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 6
Daily Stand-up Meeting Report
Week: October 9 - October 15
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Went through the latest requirements | Went through the latest requirements | Went through the latest requirements | Went through the latest requirements | Went through the latest requirements
| Going through the latest requirements | Going through the latest requirements | Going through the latest requirements | Going through the latest requirements | Going through the latest requirements
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Ashwini | 1)Worked on the mid term presentation. | 1)Worked on searching through databases. | 1)Worked on the mid term presentation comments. | 1)Worked on the mid term presentation comments. | 1)Worked on the mid term presentation comments.
| 2)Going through the database. | 2)Working on the mid term presentation comments. | 2)Working on the mid term presentation comments on test document. | 2)Working on the mid term presentation comments user documentation. | 2)Working on the mid term presentation comments installation documentation.
| 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now. | 3)No obstacles till now.
Rupanandha | 1.Working of mid term presention comments given by professor | 1.Working of mid term presention comments given by professor | 1.Working of mid term presention comments given by professor | 1.Working of mid term presention comments given by professor | 1.Working of mid term presention comments given by professor
| 2.Discussed with what needs to be done | 2.Discussed with what needs to be done | 2.Discussed with what needs to be done | 2.Discussed with what needs to be done | 2.Discussed with what needs to be done
| 3.No issues , Work is on Track | 3.No issues , Work is on Track | 3.No issues , Work is on Track | 3.No issues , Work is on Track | 3.No issues , Work is on Track
Mani | 1)Planing on the changes on documentation. | 1)Planing on the changes on documentation. | 1)Planing on the changes on documentation. | 1)Planing on the changes on documentation. | 1)Planing on the changes on documentation.
| 2)Found what are the changes need to make in documentation. | 2)Need to update all documents | 2)Need to update all documents | 2)Need to update all documents | 2)Need to update all documents
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1) Working on the changes that need to made to the documents. | 1) Working on the changes that need to made to the documents. | 1) Working on the changes that need to made to the documents. | 1)Updated the documents. | 1)Finalized the changes.
| 2)Working on the changes that need to be made. | 2) Working on the changes that need to made to the documents. | 2) Working on the changes that need to made to the documents. | 2)Finalize the changes that need to be made. | 2)Made all the required changes to the documents.
| 3)Need to make the necessary changes. | 3)Need to make the necessary changes. | 3)Need to make the necessary changes. | 3)No Issues. | 3)No Issues.
Teja | 1)Worked on alteration of the documentation. | 1) Worked on development of documentation. | 1) Started making changes to the documentation. | 1) Updated the documents with appropriate changes. | 1) Took inputs from the team and made some more changes in the document.
| 2) Worked on documentation. | 2) Looking at changes to be made in the documentation. | 2) Continued working on the changes to be made in the documentation, | 2) Made a throrough check on all the documents. | 2) Updated the document.
| 3) No major issues yet. | 3) Found out some loop holes in the documentation. | 3) No major issues yet. | 3) Had a discussion with the team members regarding the changes made in the documents, | 3) No issues yet.
Ram Naveen | 1. Submited all the documents last week. | 1. Working on technolgy which should be used in the project. | 1. Got the comments from the proffesor. | 1. Made some changes with the documents | 1. Updated some documents according to comments by the proffesor.
| 2. Worked on technolygy to use in the project. | 2. Had some brain storming session with the project. | 2. Discussed what neeeded to be done among the team. | 2. Reviwed every comment made by the proffesor. | 2. Discuused the updations among the team.
| 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now. | 3. No issues upto now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 5.
Daily Stand-up Meeting Report
Week: October 2 - October 8
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1)Check rules for signal | 1) Confirmed for 3 lights inspite of 4(protected light) | 1) Read some research papers on Traffic simulations | 1)Worked on drag and drop feature | Working on python technology
| 2) Working on the requirement of number of lights | 2) Working on the requirement of number of lights | 2)Work on created drag and drop feature | 2) Comparing Swing and other similar technologies | 2) Checking python for drag and drop
| 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet
Ashwini | 1)Worked on the test case documentation little | 1)Worked on the test case document middle level | 1)Worked on the test case documentation at to finish | 1)Worked and completed test case documentation | 1)Worked and complete the installation documentation
| 2)Working on test case documentation | 2)Working on the test case documentation | 2)Working on test case documentation | 2)Working on the installation documentation and test suite | 2)Working on the test suite document
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Working use case documenting | 1)Working on use case documentation | 1) Working on Usecase documentation | 1) Working on Usecase documentation | 1) Working on Usecase documentation
| 2)Researching Swing | 2) Researching on SWING | 2)Researching through HTML 5 | 2)Researching through HTML 5 | 2)Researching through HTML 5
| 3)No blockers | 3)No blockers | 3)No Blockers | 3)No Blockers | 3)No Blockers
Mani | 1)Started working on requirement document. | 1)completed about 80% of document along with sahil. | 1)completed requirement document. | 1)started working on presentation. | 1)Completed about 50% of ppt.
| 2)Should complete the requirements document about 70 %. | 2)should finish the requirement document. | 2)Start working on midterm presentation. | 2)complete about 50 % of ppt. | 2)Finsh midterm presentation.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Discussed the format need to be followed in the Documentation | 1)Working on the Issues Management Documentation | 1)Working on the Issues Management Documentation | 1)Completed the Issues Management Document | 1)Done with the Documentation and reserching regarding the drawbacks of using HTML5 for the UI
| 2)Working on the Issues Managemnet Document | 2)Working on the Issues Management Documentation | 2)Working on the Issues Management Documentation | 2)Gone through the Document inorder to finalise and submittion | 2)Prepare for the Presentation
| 3)No Issues till now | 3)No Obstacles | 3)No Obstacles | 3)No Obstacles | 3)Need to Submit the Documents before Deadline
Teja | 1)Looking forward to sort out all the possible complications that might arise | 1) Trying to sort the issues related to different traffic models | 1)Resolved few issues that I came across while doing work | 1)Sample prototype in progress | 1)Tried sample prototype using html5 and javascript.
| 2) Checking for loop holes in the design | 2) Working on the basic traffic system Issues that might increase complexity | 2)Implementing different tools so that it will help me keep a record all issues | 2) Implemented few techniques that I have learned | 2) Compared the work accomplished using two different technologies.
| 3)Got a clarity on which technology to use | 3) No obstacles as yet | 3)No major complications yet | 3)Discussed with the team regarding technology selection | 3) Looking forward to meeting with the client.
Ram Naveen | 1. I took the responsibility of preparing testplan and prototypes | 1. Collected a sample document on test plan | 1. Created a prototype based on project | 1. Disccussed test plans to have more ideas | 1. Presented both the documents with the team
| 2. Looked on IEEE standard document to get a basic idea | 2. Reasched on various ways to test the requiremnts | 2. Had some doubts regarding project | 2. Documented these test plans which we have discussed | 2. Had approval from the team for those requriments
| 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 4
Daily Stand-up Meeting Report
Week: September 26 - September 30
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read 2 way rules | Read 4- way rules | Read 4- way rules | Read technologies stack | Read technologies stack
| Read 4- way rules | Read 4- way rules | Read 4- way rules | Read technologies stack | Read technologies stack
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Worked on the look and feel of the project | 1) Checked few cases for testing the project | 1)Checked more cases for testing | 1)Worked on some of the testing tools | 1)Completed test cases
| 2) Checking the test cases for the project | 2) Researching more cases for testing | 2)Working on the testing tools suitable for testing | 2)Researching test cases | 2)Working on test case documentation
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents
| 2)Updating the requirement doc | 2)Reading through the depending docs | 2)Reading through the depending docs | 2)Reading through the depending docs | 2)Reading through the depending docs
| 3)No Blocker | 3)No Blocker | 3)No Blocker | 3)No Blocker | 3)No Blocker
Mani | 1)Known how to requirements document. | 1)Gone through some requirements | 1)Found the key requirements and started documenting. | 1)Started doing research on swing. | 1)Countined doing research on swing.
| 2)Should go through overview of requirements | 2)Should find the key requirements and start documenting. | 2) Should do some research on swing. | 2)should continue research on swing. | 2) should continue documenting requirements.
| 3)No issues till now. | 3)No issues till now. | 3) No issues till now. | 3)No issues till now | 3)No issues till now.
vamsy | 1)Researched all kind of issues that might occur in future. | 1)Gone through the requiremnts and found an issue. | 1)working on the tools that helps us keep track of all the issues. | 1)still working on tools. | 1)Updated some of the Issues in the Issues document.
| 2)Go through all the requiremnts in order to find the issues. | 2)Need to disscuss with the team members regarding the issue. | 2)resolved the issue that I came across last week | 2)need to finalize the tools for the issues record maintenance. | 2)Make some changes to the Issues document.
| 3)No obstacles yet | 3)Issue need to be resolved. | 3)no issues | 3)no issues | 3)No Issues.
Teja | Learning technolgies for prototype implementation | Worked on sample functions in swing and javascript | Practicing technolgies | Practicing the technologies | Continuing the practice of the technologies
| Focus is on technolgies and implementation | Practicing the technologies | Gone through swing API | Focus Shifted to html5 and javascript | Focus is on html5 and javascript
| No major complications yet | No major complications yet | No major issues | The issue of Technology selection is yet to be resolved | The issue of Technology selection is yet to be resolved
Ram Naveen | 1) Exploring various testing tools to test the project | 1) Selecting some software tools wich would useful to project | 1)Working on testing tools and forwarding to group members | 1)Working on testing tools and forwarding to group members | 1) Working on Creating test plans
| 2) Watching videos about swing to get basuc idea | 2)Looking forward to discuss among team members about tools in next meeting | 2) Learning on swing through tutorials | 2)2) Learning on swing through tutorials | 2) Had some doubts on HTML5
| 3. No obstacles till now | 3) No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)Need to talk in next meeting
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 3
Daily Stand-up Meeting Report
Week: September 19 - September 23
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read Reoundabout rules | Read Reoundabout rules | Read Signals rules | Read Signals rules | Read 2 way rules
| Read Reoundabout rules | Read Signals rules | Read Signals rules | Read 2 way rules | Read 2 way rules
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Learned swing until containers | 1) Worked on sample application | 1)Worked on sample application | 1)Worked on sample application | 1)Worked on sample application
| 2) Started working on sample application in swing | 2)Working on sample application in swing | 2)Working on sample application in HTML5 | 2)Working on sample application in HTML5 | 2)Working on look and feel of the project
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck
| 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers
Mani | 1)Attended client meeting and discussed about requirements. | 1) Went through some parts of traffic modelling system. | 1)Got to know how the system works. | 1) Gone through some of the prototypes. | 1)Got some finalized prototypes.
| 2)Need to go through some previous traffic modelling system. | 2) Should go through this modellling system in depth. | 2)Should see some prototypes of the traffic modelling system. | 2) Should finalize some prototypes amound which I reviewd. | 2)Should know how to write requirements document.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Attended the Client Meeting and got some of the Issues resolved | 1)Documented the changes that are made Client Requirements Document. | 1)Gone through the Tools for the implementation. | 1)Worked on the Prototypes | 1)Workedon the Prototypes
| 2)Should document the changes made to the Client Requirements Document. | 2)Should go through the possible tools for the implementation. | 2)Should study the Tools for the implementation. | 2)Should work on the Prototypes | 2.)Attend the Client Meeting.
| 3)No Issues | 3)No Issues. | 3)No Issues | 3)No Issues. | 3)No Issues.
Teja | Analyzed the inputs for the project in a clear way | Trying to decide what inputs are unnecessary | Analyzing various techniques useful for the project | Trying to analyze different technologies | Had gathered useful information from the client
| Studying through the client requirements | Studying through the client requirements | Documenting requirements | Trying to learn the technologies useful for building the project | Learning the technologies
| No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet
Ram Naveen | Decided to do some sample prototypes | 1. Working on sample prototypes | 1.Shared sample prototypes among team. | 1. Working on test tools which are useful for project | 1.Had a proposal about HTML5
| 2. Discusssed among team. | 2. Developed some sample prottypes | 2. Disussed on testing tools to use. | 2. Gone through various tes cases. | Sheduled client meeting to discuss with client
| 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 2
Daily Stand-up Meeting Report
Week: September 12 - September 16
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read continuous event simulation sys | Read Coffee Script | Go through Missouri laws | Read github | Read github
| Read Coffee Script | Go through Missouri laws | Read github | Read github | Read github
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Started learning Swing | 1)Installed the swing on my laptop | 1)Learned swing until event handling | 1)Learned swing until event listeners | 1)Learned swing until layouts
| 2)Installing the swing on my laptop | 2)`Learning swing until event handling | 2)Learning swing until event listeners | 2)Learning swing until layouts | 2)Learning swing until containers
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding
| 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers
Mani | 1) Got some idea of the project from first client meeting. | 1)Got some knowledge on event simlation. | 1)Got to known somemore about Event Simulation. | 1)Started working on discrete event simulation. | 1)Got some more knowledge on discrete event simulation.
| 2)Should study on event simulation. | 2)should get some more knowledge on event simulation. | 2)Should start working on discrete event simulation. | 2)should improve my knowledge on discrete event simulation. | 2)Should attend client meeting.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Got to know the requirements of the client. | 1)Gone through the requiremts document. | 1)Done some research on the requirements. | 1)Discrete Event Simulation | 1)Got some more knowledge on discrete event simulation.
| 2)Should go through the client requiremnts. | 2)Should do some reserach whether all the requiremnets are possible for implementation. | 2)Discrete Event Simulation | 2)Should get some more knowledge on Discrete Event Simulation | 2)Client meeting
| 3)Should get to know all the possible cases from the Client Requirements. | 3)Should get to know all the possible cases from the Client Requirements. | 3)Should get to know all the possible cases from the Client Requirements. | 3)No issues | 3)No Issues
Teja | Trying to analyze the project requirements | Analyzing inputs for the project | Documenting all the inputs required for the project | Analyzing the design the of the project | Researching about simulation
| Researching on swing technology | Studying the implementation of existing system | Studying the implementation of existing systems | Checking whether the existing techniques are useful for the project or not. | Learning the techniques useful for simulation
| No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet. | No obstacles yet
Ram Naveen | 1. Have searched about existing system | 1. Proffesor sugested on swing and java | 1. Every one are new to the swing software | 1. Working on swing tutorial | 1. Looking some videos on swing tutorial
| 2. No obstacles yet. | 2, Had a convesation on technology | 2. Decided to work on swing | 2. Learning swing tutorial | 2. Looking on projects which are based on swing
| 3. No obstacles till now | 3. No obstacles yet | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 1
Daily Stand-up Meeting Report
Week: September 5 - September 9
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read about Discrete Event Simualtion | Read some research papers | Read continuous event simulation sys | Read about Requirement gathering documents | Go through the existing system
| Read some research papers | Read continuous event simulation sys | Read about Requirement gathering documents | Go through the existing system | Read continuous event simulation sys
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Read the articles regaring the project | 1) Got to now a little about the project | 1)Got the clear idea of the project | 1)Worked on checking the UI | 1)Checked the UI of drop down of different sites
| 2)Understanding the project and client expectations | 2)Understanding the project and client expectations | 2)Started checking the UI of exsisting traffic websites | 2)Checking the UI of drop down of exsisting sites | 2)Checking the UI of button of various websites
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project
| 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems
| 3) No Blockers | 3) No Blockers | 3) No Blockers | 3) No Blockers | 3) No Blockers
Mani | 1)Got to know the project and roles. | 1)known about the roles | 1)Just known about traffic systems and their importance. | 1)Got a very breif idea about traffic systems. | 1)Gone through some traffic rules.
| 2) yet to decide roles. | 2) Trying to understand the project. | 2)Trying to know more about traffic systems. | 2)Studied some traffic rules. | 2)should attend a meeting with the client.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Assigned the roles to all the team members | 1)Got to know about my role. | 1)Studied some of the presently available Traffic Simulation Softwares | 1)Done some research regarding the requrements for the project. | 1)Wrote down some of the key constraints.
| 2)Got to know about my role. | 2)Stould study some of the presently available Traffic Simulation Softwares | 2)Should do some research regarding the requrements for the project. | 2)Should write down the key Constraints that need to be considered. | 2)Attend the Client meeting Should ge a clear understanding of the project requirements.
| 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)No obstacles.
Teja | Got to know about my role. | Trying to analyze the requirements of project | Reading the implementations of existing systems | Reading the implementations of existing sytems | Learning through existing systems
| Researched on exisiting systems | Researching technologies for implementation | Learning the implementation techniques | Learning implementation techniques | Jotted down all the important techniques from various sources
| No obstacles yet | No major obstacles yet | No major complications yet | No obstacles upto now | No obstacles upto now
Ram Naveen | 1. Based on client meeting we have researched about project | 1. Had some research on existing system | 1. Professor said about project | 1. Shared our views | 1. We had a client meeting.
| 2. Discussing on requiirements | 2. Decided to do some more work on exising system | 2. We searched on various site about project | 2. Had some research on traffic rules | 2. Came to know about the project
| 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?