## Sheet1
Ekathra_Team B Weekly Iteration Plan
Weeks | Date | Module 1 | Module 2 | Module 3 | Module 4 | Module 5
Week 1 | 2017-01-13 | Iteration plan, architecture planning | NA | NA | NA | NA
Week 2 | 2017-01-20 | Creating multiple screens for traffic modelling system | Car generation sudo code | Drag and drop feature sudo code | NA | NA
Week 3 | 2017-01-27 | Create simulation screen for the project | Sudo code for loading default values | Implementing drag and drop on road types | NA | NA
Week 4 | 2017-02-03 | Designing algorithm for inputting 12 input values per junction | Working on car properties, Completing setting speed | Code for generating roundabout | NA | NA
Week 5 | 2017-02-10 | Writing code for single road if user selects nothing | Acceleration and deceleration variation of cars | Code for stop signs road type for 2 way and 4 ways | NA | NA
Week 6 | 2017-02-17 | Designing algorithm for setting defaults for all car generators | Using buffer for avoiding collisions | Code for signalling road type | NA | NA
Week 7 | 2017-02-24 | Writing code aucto direction of cars at all the junctions | Allocating directions for the car | Code for T junction road type | NA | NA
Week 8 | 2017-03-03 | NA | Integrating car generator for every road type | Integration for all road types | Car garbage collection | NA
Week 9 | 2017-03-10 | NA | NA | NA | Storing the simulation Details | Unit Testing for every module, documentation
Week 10 | 2017-03-17 | NA | NA | NA | Adding required additional features for the storing values | Unit Testing for every module, documentation
Week 11 | 2017-03-24 | NA | NA | NA | NA | Integration testing
Week 12 | 2017-03-31 | NA | NA | NA | NA | Fixing Bugs for the code, Integrating again and fixing bugs
Week 13 | 2017-04-07 | NA | NA | NA | NA | Complete Project Testing
Note1: Integration and testing for evrey module is done for every two weeks to track the status of the project.
Note2 : From the week 13 we will have buffer time to modify and develop the code from the changes made by the client after demonstration of project.
Mapping
Module1 | Architecture Design
Module 2 | Car generation development
Module 3 | Roads & roads integration
Module 4 | Car Garbage Selection
Module 5 | User,Unit, and Integration testing,documentation