## Week 12
Daily Stand-up Meeting Report
Week: March 26 - April 1
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on 2 D layout | 1) Refacot the code | 1) Worked on documents | 1) Worked on documents | 1)Fixing bugs
| 2) Refactor the code | 2) Worked on 2 D layout | 2) Worked on documents | 2) Worked on documents | 2) Fixing bugs
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | 1)Working on the test plan modification | 1)Worked on updating test cases | 1)Worked on test cases | 1) worked on manual testing | 1)worked on documentation
| 2) Working on updating test cases | 2) Performing test cases | 2) Performing manual testing on the project | 2)working on the documentation | 2) working on documentation
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Completed code cleaup | Started working on bug fixes resulted after code merge | Continued working on bug fixes resulted after code merge | Completed working on bug fixes resulted after code merge | Started working on test cases failures
| No Blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1) worked on 2 -d layout intration | 1) worked on popup windows for inputs | 1) worked on popup windows for inputs | 1) testing on code | 1) worked on artifacts for submission
| 2) should work on popup windows | 2) should work on popup windows | 2) should start testing of the code | 2) working on artifacts | 2) working on artifacts
| 3) No issues | 3) No issues | 3) No issues | 3) No issues | 3) No issues
vamsy | Completed code cleaup | Started working on bug fixes resulted after code merge | Continued working on bug fixes resulted after code merge | Completed working on bug fixes resulted after code merge | Started working on test cases failures
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Have continued working on the integrated code. | Checked for any bug fixes. | Continued testing the integrated code with all test cases. | Worked on the acceleration and deceleration part for minor changes. | Had a final check on the integrated code.
| Tested the integration of the code. | Made sure if there any bugs in the code. | Checked the testcases. | Tested the algorithm with changes. | Tested the integrated integrated code for all test cases.
| No major issues found | No major issues found. | No major issues found. | No major issues found. | No major issues found.
Ram Naveen | 1. Had an issue at the circular junction about its direction. | 1. Discussed about the cient meeting. | Has to implement some validations. | 1. Discussed with the team about the issues after the testing. | 1. Done some documnetation
| 2. Shown the code with the client. | 2. Tested some cases and found that they are failed. | Founded that validations are failed in some cases. | 2. Reviewd the documents that need to be submitted. | 2. Submitted documents for the final presentation.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 11
Daily Stand-up Meeting Report
Week: March 19 - March 25
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on designing GUI part of signaling road component | 1) Worked on 2 D layout | 1) Worked on 2 D layout | 1) Worked on designing GUI part of signaling road component | 1) Worked on sign symbol of signaling road component
| 2) Worked on designing GUI part of signaling road component | 2) Worked on getDraggableSignalRoadPanel() and valueSetter() | 2) Worked on 2 D layout | 2) Worked on sign symbol of signaling road component | 2) Worked on sign symbol of signaling road component
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | 1)Worked on research of command window | 1) Worked on loading default values | 1)Worked on inputs code implementation | 1)integrated inputs code with 2-D layout upto now and found some issues | 1)Worked on issues
| 2)working on loading default values | 2)implemented the code for taking input values | 2)integrating inputs code with 2-D layout upto now | 2)Working on fixing the issues. | 2)Testing the project till now
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Continued working Commander class with methods getJPanel1,getJButtonStart getJButtonStop which are responsible taking inputs from the user to generate the cars on road and to start and stop the simulation. Similarly getJButton1 to getJButton 2 these are responsible for taking inputs from the ser on each intersection , how many cars should go on each side(East, West, North, South). | Continued working on Created a Commander class with methods getJPanel1,getJButtonStart getJButtonStop which are responsible taking inputs from the user to generate the cars on road and to start and stop the simulation. Similarly getJButton1 to getJButton 2 these are responsible for taking inputs from the ser on each intersection , how many cars should go on each side(East, West, North, South). | Completed working on Commander class with methods getJPanel1,getJButtonStart getJButtonStop which are responsible taking inputs from the user to generate the cars on road and to start and stop the simulation. Similarly getJButton1 to getJButton 2 these are responsible for taking inputs from the ser on each intersection , how many cars should go on each side(East, West, North, South). | I have worked on a lot of stuff around the project during the spring break, and I have introduced a lot of the code some of it is used for the project a most did not.I left all those code and files, which is creating a lot of confusion to understanding.My first task is to clean up that stuff I started working on code clean up | Cintinued working on code clean up
| No Blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1) integration of collision dectecion class | 1) worked on 2-d layout | 1) worked on 2-d layout | 1) worked on 2-d layout | 1) worked on 2-d layout
| 2) Should work on 2-d layout | 2) Should work on 2-d layout | 2) Should work on 2-d layout | 2) Should work on 2-d layout | 2) Should work on 2-d layout
| 3) No issues | 3) No issues | 3) No issues | 3) No issues | 3) No issues
vamsy | Checked the code thoroughly for changes. | Continued working on the testing. | Started intergrating the code with acceleration and deceleration. | Continued with the integration of code. | Tested a part of integrated code to ensure proper working.
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Checked the code thoroughly for changes. | Continued working on the testing. | Started intergrating the code with acceleration and deceleration. | Continued with the integration of code. | Tested a part of integrated code to ensure proper working.
| Found some bugs and fixed them. | Tested all methods associated with collision detection. | Found few issues and made some changes | Continued with integration. | Tested all parts of the code.
| No major issues found. | No major issues found. | No major issues. | No major issues found. | No major issues found.
Ram Naveen | 1. Worked on xml file for the 2-D layout. | 1. made 2-D layout looks in a appropriate way. | Fixed the bugs that has rised after the integration. | 1. used the prototype code to design a appropriate showing of the car. | 1. Used default values at every juntion and at every landing.
| Designed 2-D layout in it signals and stop signs. | 2. Designed and implemented all the algorithms with the 2 D layout.. | 2. made code clean up | 2. At every intersection with respect to the east west north south, made some default values. | 2. Continued with the use of default values.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 10
Daily Stand-up Meeting Report
Week: March 12 - March 18
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on signaling road component | 1) Worked on signaling road component | 1) Worked on challenges regarding the GUI | 1) Worked on challenges regarding the GUI | 1) Worked on getDraggableSignalRoadPanel() and valueSetter()
| 2) Worked on signaling road component | 2) Worked on signaling road component | 2) Worked on challenges regarding the GUI | 2) Worked on getDraggableSignalRoadPanel() and valueSetter() | 2) Worked on getDraggableSignalRoadPanel() and valueSetter()
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | 1) worked on integration. | 1)worked on bugs | 1)worked on 2-D layout | 1)worked on loading default and input values | 1)worked on 2-D layout for 2 way
| 2)working on testing project and fixing bugs | 2)working on the 2-D layout pattern | 2)working on how to load default values and inputs | 2)working on 2-D layout for 4 way | 2)working on 2-D layout
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Created test case named CarTracingTest to test the CarTracking functionality.The test case contains two methods to check the length of the list is updating as per the business on addition and removal of the car. | Continued working on test case named CarTracingTest to test the CarTracking functionality.The test case contains two methods to check the length of the list is updating as per the business on addition and removal of the car. | Completed tested case and started integrate the and test the function CarDistribution and CarTracking together | Continued integrating the and test the function CarDistribution and CarTracking together | Completed integrate the and test the function CarDistribution and CarTracking together and Created a Commander class with methods getJPanel1,getJButtonStart getJButtonStop which are responsible taking inputs from the user to generate the cars on road and to start and stop the simulation. Similarly getJButton1 to getJButton 2 these are responsible for taking inputs from the ser on each intersection , how many cars should go on each side(East, West, North, South).
| No Blocker | No Blocker | No Blocker | No Blocker | No Blocker
Mani | 1) worked on stop distance class | 1) worked on collison detection algorithm | 1) worked on collison detection class | 1) worked on collison detection class | 1) worked on collison detection class
| 2) should work on collision detection mechanism | 2) Shoulc code collistion detection class | 2) Continue working on collison detection class | 2) Continue working on collison detection class | 2) Continue working on collison detection class
| 3) No issues | 3) No issues | 3) No issues | 3) No issues | 3) No issues
vamsy | 1. Decided to work on car speed display. | 1. Developed code to update instace of the car at every second | 1. Worked on distribution of car at each junction. | Had a blocker about the percentage distribution. | Discussed with team about the abother approach
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Started implementing the algorithm suggested by proffessor. | Continued working on obstacle detection. | Continued working on the collision formulae. | Tested the working of the formulae. | Verified the working of the algortihm.
| Conitinued integrating formulaes for different parts. | Dealth with few blockers. | Implemented the formulae programatically. | Implemented the formulae with different approach. | Cross checked the code and started integration.
| No major issues were found. | No major issues. | No major issues. | No issues were found. | No major issues were found.
Ram Naveen | 1. Decided to work on car speed display. | 1. Developed code to update instace of the car at every second | 1. Worked on distribution of car at each junction. | Had a blocker about the percentage distribution. | Discussed with team about the abother approach
| 2. worked on displayiong spped of the car on the car. | 2. worked on code development. | 2. Developed code for distribution. | Made changes accordingly in the code. | Team has approved the another approach
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 9
Daily Stand-up Meeting Report
Week: March 5 - March 11
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on signaling road component. | 1) Worked on signaling road component. | 1) Worked on DraggableSignalRoadPanel class | 1) Worked on getDraggableSignalRoadPanel() and valueSetter(). | 1) Worked on getDraggableSignalRoadPanel() and valueSetter().
| 2) Worked on signaling road component. | 2) Worked on DraggableSignalRoadPanel class | 2) Worked on getDraggableSignalRoadPanel() and valueSetter(). | 2) Worked on getDraggableSignalRoadPanel() and valueSetter(). | 2) Worked on getDraggableSignalRoadPanel() and valueSetter().
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | 1) worked on deceleration code | 1)worked on the stop distance code | 1)worked on the break distance code | 1) worked on the collision algorithm | 1)worked on the collision algorithm
| 2) working on the stop distance code | 2) working on break distance code | 2)working on the collision algorithm | 2) working on collision algorithm | 2)working on the collision algorithm
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Continued working on CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes | Continued working on CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes | Continued working on CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes | Continued working on CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes | Completed CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes
| No Blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1) cleaned up the code | 1) Worked on the workshop presentation | 1) Worked on the workshop presentation | 1)partially coded brake distance class | 1) completed coding brake ditance class
| 2) Working on the workshop presentation | 2) continued Working on the workshop presentation | 2)Code brake distance class | 2) complete brake distance class | 2) work on stop distance class
| 3) no issues | 3) no issues | 3) no issues | 3) no issues | 3) no issues
vamsy | 1) Worked on signaling road component. | 1) Worked on signaling road component. | 1)worked on the break distance code | 1) worked on the collision algorithm | 1)worked on the collision algorithm
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Continued working on collision detection. | Continued working on the car collision research. | Worked on the collision detection modifications. | Worked on collision detection using an approach suggested by professor. | Elaborated the formula suggested by the proffessor.
| Researched about different approaches to collision detection. | Tried out new methods associated with the collision. | continued changing the code. | Continued working on the same approach. | Have done a deep research on that approach.
| No major issues were found. | No major issues were found. | Had some minor issues. | No major issues found. | No major issues were found.
Ram Naveen | 1. Developed formula for breaking distance | Prepared a sample diagram on 2-D layout that has to show. | 1. Completed the acceleration and decceleration module. | 1. Preparedsome code on collision algorithm on calculating the before car distance the car has to stop. | 1. Made a team meeting on 2-D layout that has to be implemented.
| 2. discussed with the team about posssibility the formula. | 2. worked on stopping distance that the car has to stop before the car. | 2. moved to collision algorithm module | 2. Worked on coding of collision algorithm. | 2. cheked the collision algorithm with car acceleration and decceleration..
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 8
Daily Stand-up Meeting Report
Week: February 26 - March 4
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on getTwoWayRoadComponent(), valueSetter() | 1) Refactor the existing code | 1) Setter methods for setting the screen size | 1) Refactor the existing code | 1) Setter methods for setting the screen size
| 2) Refactor the existing code | 2) Setter methods for setting the screen size | 2) Refactor the existing code | 2) Setter methods for setting the screen size | 2) Worked on getTwoWayRoadComponent(), valueSetter()
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | )Worked on integration of project for milestone 2 | 1)Worked on issues for milestone 2 | 1)worked on the issues fixing | 1)Worked on acceleration code | 1)worked on acceleration code
| 2) Working on issues | 2) Fixing the issues for milestone 2 | 2) Started working on the acceleration code as suggested by the profesor | 2)working on acceleration code | 2)working on the deceleration code
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Worked on milestone 02 demo meeting with professor on Wednesday and as well as project status meeting with the professor | Continued Working on milestone 02 demo meeting with professor on Wednesday and as well as project status meeting with the professor | Dumped existing code and started a new approach and created Created two LinkedList's for north to south bound and west to east bound and creatd two method addCar and removeCar method for updating the positions on the change of direction in intersection | Continued Creating two LinkedList's for north to south bound and west to east bound and creatd two method addCar and removeCar method for updating the positions on the change of direction in intersection | Continued working on CarTracker class with two methods addCar and removeCar, these two methods manipulates the northsouthLinkedList and eastwestLinkedList and maintains the car count appropriately according to the direction changes
| No Blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1) Should work on milestone 2 demo | 1) milestone 2 demo | 1) working on car garbage system | 1) working on car garbage system | 1)Integration
| 2) milestone 2 demo | 2) Car garbage system | 2) Car garbage system | 2) Integration | 2)Planning on cleaning up the code
| 3) no issues | 3) no issues | 3) no issues | 3) no issues | 3) no issues
vamsy | 1) Should work on milestone 2 demo | 1) milestone 2 demo | 1) working on car garbage system | 1) working on car garbage system | 1)Integration
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Completed the work associated with the parser. | Added few methods to the acceleration and deceleration part of code. | Worked on the other classes related to traffic signals. | Worked on the bugfixes in both the codes. | Made sure the integration of all these classes was correct.
| Tested the parser to ensure fine working. | Modified the methods inorder to ensure proper acceleration. | Added the required methods. | Verified whether everything is correct. | Continued working on integration.
| No issues were found. | No issues were found with acceleration. | No major issues were found. | No major issues found. | No major issues found.
Ram Naveen | 1. Had a client demo and discussed about what to show to the client. | 1.Resolved some issues that has to shown for milestone 2 | 1. Had meeting with the client. | 1. Discussed about the output of the client meeting with the group. | 1. Made desions on project and worked as group.
| 2. Documneted the issue that are to be discussed with the client. | 2. Had checked the final version that need to present for the milestone 2. | 2. Client has suggested some approaches and removed drag and drop feature. | 2. Had prepared a working plan and possibilities of it. | 2. Worked on possibility of linked lists with cars
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 7
Daily Stand-up Meeting Report
Week: February 19 - February 25
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked DraggableTwoWayPanel component | 1) Created setter and getter methods | 1) Worked on completing project documents | 1) Refactor the code | 1) Fix fix related to screen size
| 2) Worked on DraggableTwoWayPanel component | 2) Worked on completing project documents | 2) Worked on DraggableTwoWayPanel component | 2) Worked on completing project documents | 2) Refactor the code
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Ashwini | 1)Worked on the mid-term presentation | 1)Worked on collision algorithm | 1)Worked on fixing the bugs | 1)Worked on collision algorithm | 1)Worked on acceleration and deceleration code integration, testing and modification
| 2)Working on the collision algorithm | 2)Working on fixing the bugs | 2)Working on collision algorithm | 2)Working on acceleration and deceleration code integration, testing and modification | 2)working on fixing the issues.
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Code integration resulted in issue[CarSpeed is not increasing automatically and a car is getting overlapped] in simulation functionality | Continued code integration resulted in issue[CarSpeed is not increasing automatically and a car is getting overlapped] in simulation functionality | Continued code integration resulted in issue[CarSpeed is not increasing automatically and a car is getting overlapped] in simulation functionality | Continued code integration resulted in issue[CarSpeed is not increasing automatically and a car is getting overlapped] in simulation functionality | Completed code integration resulted in issue[CarSpeed is not increasing automatically and a car is getting overlapped] in simulation functionality
| Blocker unable to pass the car object from one JPanel to another JPanel.On passing from one JPanel to another JPnel Car object is getting initialized to the default values instead of holding the current state | Continued woriking on blocker unable to pass the car object from one JPanel to another JPanel.On passing from one JPanel to another JPnel Car object is getting initialized to the default values instead of holding the current state | Continued woriking on blocker unable to pass the car object from one JPanel to another JPanel.On passing from one JPanel to another JPnel Car object is getting initialized to the default values instead of holding the current state | Continued woriking on blocker unable to pass the car object from one JPanel to another JPanel.On passing from one JPanel to another JPnel Car object is getting initialized to the default values instead of holding the current state | Completed fixing blocker unable to pass the car object from one JPanel to another JPanel.On passing from one JPanel to another JPnel Car object is getting initialized to the default values instead of holding the current state
Mani | 1) integration | 1)solved issues with car speeding | 1) interation | 1)Itegration of car module with acceleration and speeding. | 1) claening some code
| 2)Itegration of car module with acceleration and speeding. | 2) continue integartion | 2) Tesing the car speeding and acceleration | 2) do some clean up in code | 2)monday submission
| 3) some issues with car speeding. | 3) no issues | 3) No issues. | 3) no issues | 3) no issues.
vamsy | Continued working on the collision detection algorithm. | Continued to work on changes in the acceleration and deceleration code. | Acceleration and deceleration code modifications were tested. | Worked on parsing the default values using json parser | Continued extracting the default values using parser.
| No major issues. | No major issues. | No major issues. | No major issues. | No major issues.
Teja | Continued working on the collision detection algorithm. | Continued to work on changes in the acceleration and deceleration code. | Acceleration and deceleration code modifications were tested. | Worked on parsing the default values using json parser | Continued extracting the default values using parser.
| Made some changes to acceleration and deceleration code. | Worked on the collision detection formulae to ensure proper working. | Changes were made to crucial parts of the code. | Tested whether the parser is working correctly. | Tested the obtained results and verified if they were correct.
| There were some issues related to collision dectection. | Had few issues with the algorithm. | No issues related to acceleration and deceleration. | No major issues with the parser. | No major issues.
Ram Naveen | 1.Worked on fixing car acceleration and decceleration module. | 1. Discusssed with the team about the issue | 1. Decided to develop rank genration algorithm. | 1. Used this rank generation algorithm with the car module | Used car class to make car visible on the j panel
| 2. Had a issuue of ovelapping of cars on every car. | 2. worked on threads to resolve the issue | 2. Developed rank generator algorithm at the stop signs | Added some more instances for the car class, arrival and departure time for the car. | Worked on calculating car departure and arrival time.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 6
Daily Stand-up Meeting Report
Week: February 12 - February 18
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Recreated the car module as the old car module did not work | 1) Recreated the car module as the old car module did not work | 1) Worked on the Static module for Two way road component | 1) Worked on the Static module for Two way road component | 1) Fix the bugs in the existed code
| 2) Fix the bugs in the existed code | 2) Integrated the "Car" module with exisited code | 2) Fix the bugs in the existed code | 2) Worked on the Static module for Two way road component | 2) Fix the bugs in the existed code
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1) Worked on the integration. | 1) Worked on the research of the collision detection algorithm | 1)Worked on the collision detection algorithm | 1)Worked on the collision detection algorithm and updated iteration plan | 1)Worked on the mid-term presentation documents.
| 2) Research on the collision detection algorithm | 2)Working on the collision detection algorithm and and updating iteration plan | 2)Working on the collision detection algorithm and and updating iteration plan | 2)Working on the documents for the mid-term presentation. | 2)Working on the documents for submission
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
Rupanandha | Completed code for path generation | Continued coding for Car distribution | Continued coding for Car distribution | Worked on intregartion | Worked on intregartion
| Started coding for Car distribution | NO Blockers | NO Blockers | Resolved the integration issues | Resolved the integration issues
| No Blockers |  |  | No Blockers | No Blockers
Mani | 1) Working with integration. | 1) Partially tested integrated code. | 1) Solved some of the issues founded. | 1) Made code corrections. | 1) Worked on interation.
| 2) Will be testing the integarted code. | 2) Will solve issues found. | 2) Prepare code for Client meeting. | 2) Will be working on integration of accleration and sppeding code. | 2) Continue working on integration.
| 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now. | 3) No obstacles till now.
vamsy | 1)Working on Integration. | 1)Tested the integrated code | 1)Solved the issues found | 1)Code changes | 1)Worked on Integration
| 2)Test the integrated code | 2)need to solve some issues | 2)prepare code for the first client meeting for milestone | 2)integration of accelration and speeding code | 2)working on Integration
| 3)No Obstacles | 3)Some issues found during code testing. | 3)No Obstacles | 3)No Obstacles | 3)No Obstacles.
Teja | 1) Working on integration of code | 1) Have reviewed the integrated code. | 1) Found some solutions on how to deal with collisions | 1) Reviewing the changed code. | 1) Working on collision detection
| 2) Research on obstacle detection | 2) Further research on dealing with obstacle detection | 2) Trying out some changes in the code | 2) Testing the code for all test cases | 2) Trying to make it work with all test cases
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles | 3) No obstacles | 3) No major obstacles.
Ram Naveen | Done the integration of road type and car generation module, | Made changes regarding the code to work on. | Met each other to discuss about presentation to the client. | Discussed about the client demonstration | Made some changes after the integration of the project.
| Worked on fixing bugs after the integration. | Had the integrated code to demonstrate with the client. | Given client demonstration and client had made some comments about the project. | Integrated code on car acceleration and deceleration part. | Working on fixing the bugs after the integration of car acceleration and decceleration.
| No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 5
Daily Stand-up Meeting Report
Week: February 05 - February 11
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on the draggable T junction panel | 1) Worked on the T junction panel and created StaticTJunction class for it | 1) Fix the bugs in the existed code | 1) Integrate car module with road components | 1) Refactor the class SecondScreen code
| 2) Worked on the static T junction panel | 2) Worked on the T junction panel and especilly StaticTJunction class for it | 2) Integrate car module with road components | 2) Refactor the complete code | 2) Fix the bugs in the existed code
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1)Researched on the car acceleration algorithm. | 1)Worked on the car acceleration algorithm. | 1)Worked on the car acceleration algorithm. | 1) Researched on the car deceleration algorithm. | 1)Worked on the car deceleration algorithm.
| 2)Working on the car acceleration algorithm. | 2)Working on the car acceleration algorithm. | 2)Research on the car deceleration algorithm. | 2)Working on the car deceleration algorithm. | 2)Working on the car deceleration algorithm.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Rupanandha | Contiued writing the test car for car acceleratiion | Completed the test case and tested the code | Stated implementing code for Path genertion | Continued Implementing code for Path genertion | Continued Implementing code for Path genertion
| No Blockers | No blockers | No Blockers | No Blockers | No Blockers
Mani | 1)Developed car generation class. | 1) Working on dividing classes. | 1) Planning on interation of car and roads. | 1) working on integartion. | 1) working on integartion.
| 2) will be dividing the classes. | 2) Will finish that work. | 2) will be working on interation. | 2) Countiuing interation. | 2) Countiuing interation.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
vamsy | 1)Car Generation Class | 1)Working on dividing the classes | 1)Worked on intregraion of cars and roads | 1)Worked on Integration. | 1)resolved some issues found during code integration
| 2)need to divide the classes. | 2) Still working on the classes | 2)Need to work on integration of code | 2)Work on Issues | 2)Update the documents.
| 3)No Obstacles | 3)No Obstacles | 3)No Obstacles | 3)No Obstacles | 3)No Obstacles
Teja | 1) Researched on car displacement and velocity integration | 1) Worked on the displacement algorithm | 1)Continued working on velocity algorithm | 1) Worked on acceleration and velocity integration. | 1) Started research on collision detection
| 2) Working on changes in the displacement algorithm | 2) Research on velocity change of the car | 2) Completed work on velocity algoritm | 2) Testing it for all the test cases. | 2)Working on the integrated code
| 3) No major obstacles. | 3) No obstacles till now | 3) No obstacles till now. | 3) No obstacles till now | 3) No obstacles till now
Ram Naveen | Fixing bugs on integrated code. | Developed some code based on coordinates to change direction. | Developed algorithm to turn direction of the car. | Worked on direction class of the car. | Discussed our project progress with client.
| Calculaed the coordinate lenths to turn direction at the intersection. | Discussed with the team about the progress of my module. | Worked on direction class for the car. | Provided some usefull stuff to the acceleration module of the project. | Client asked about the integration, so started working ob integrating thhe code.
| No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 4
Week: January 29 - February 4
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Starting working on 4 way road component | 1) Created class for 4 way road components | 1) Worked on 4 way road component | 1) Fix the bugs in the existed code | 1) Worked on Static road panel
| 2) Created class for 4 way road components | 2) Worked on 4 way road component | 2) Fix the bugs in the existed code | 2) Worked on Static road panel | 2) Worked on Static road panel
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1)Researched on the car displacement algorithm. | 1)Researched on the car displacement algorithm. | 1)Researched on the car displacement algorithm. | 1)Worked on the car displacement algorithm | 1)Worked on the car displacement algorithm
| 2) Reseaching on the car displacement algorithm | 2) Reseaching on the car displacement algorithm. | 2) Working on the car displacement algorithm | 2) Working on the car displacement algorithm | 2) Reseaching on the car acceleration algorithm
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Rupanandha | Started coding for car acceleration Module | Implementing the code for car accleration module | Implementing the code for car accleration module | Implementing the code for car accleration module | Imlemented a test case to test the car accleartion
| No blockers | No Blockers | No Blockers | No Blockers | No Blockers
Mani | 1) Started working on car generation. | 1) Working on car generation. | 1) Working on car generation. | 1) Working on car generation. | 1) Working on car generation.
| 2) Will be contiuing development. | 2) Will be contiuing development. | 2) Will be contiuing development. | 2) Will be contiuing development. | 2) Will be contiuing development.
| 3) No blockers | 3) No blockers | 3) No blockers | 3) No blockers | 3) No blockers
vamsy | 1)Done with the presentation. | 1) Car Generation Code | 1)Car Generation Code | 1)Car Generation Code | 1)Car Generation Code
| 2)Continue the car generation development | 2)Continue Development | 2)Car Generation Code | 2)Car Generation Code | 2)Car Generation Code
| 3)No Obstacles. | 3) No Obstacles | 3) No Obstacles | 3) No Obstacles | 3) No Obstacles
Teja | 1) Finished the displacement module | 1) Research on velocity algorithm | 1) Started reviewing my own work | 1) Continued researched on integration of velocity and acceleration | 1) Further research on integration of velocity and acceleration
| 2) Researched on velocity algorithm | 2) Continued working on integration of velocity module with displacement | 2) Checked the module for any changes | 2) Completed the module based on displacement of car with few changes | 2) Started working on changes in velocity module
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now. | 3) No obstacles till now.
Ram Naveen | Made some changes with the code but didnt work | Discussed issue with the team. | Developed aan algorithm to change the speed of the road. | Worked on speed of car based on road. | Integrated code with road module.
| Provided my code to rupanandh to implement it. | worked on how to change speed based on road type. | Wrote code on speed of the car. | Integrated code with the roads module. | Worked on fixing the bugs after the integration.
| No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now. | No obstacles till now.
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 3
Daily Stand-up Meeting Report
Week: January 22 - January 28
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Worked on simulation panel | 1) Fix the bugs in the existed code | 1) Worked on simulation panel | 1) Worked on simulation panel and created method liek prepareGUI() | 1) Worked on simulation panel on the prepareGUI() method
| 2) Worked on simulation panel | 2) Worked on simulation panel and created SecondScreen class, DropTargetPanel, DraggableFourWay classes | 2) Work on 4 way module | 2) Worked on simulation panel and added some features on it | 2) Fix the bugs in the existed code
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1)Researched on loading default values | 1)Researched on loading default values. | 1)Researched on loading default values | 1)Worked on loading default values | 1)Worked on loading default values
| 2) Research on loading default values. | 2) Research on loading default values. | 2) Working on loading default values. | 2) Working on loading default values. | 2) Working on loading default values.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Rupanandha | Disscued about the UML with Fellow teammate | Made Some change to UML with respect to the other modules since its not satisfying the whole app purpose | Contiitecture of the working on UML changes to finalized the Architecture of the App | Finalized the architecture and frezeed the chages | Worked with the fellow team mate on work sharing
| Discussed about the module interactions with respect to UML | No Blockers | No Blockers | No Blockers | Continued working on the module coding
| No Blockers |  |  |  | No Blockers
Mani | 1) Finished car deceleration code. | 1) Started integrating both codes | 1) Finished working on integration. | 1) Editied it and assigned new work to everyone. | 1) Learned swing basics.
| 2) Integrating both codes. | 2) Still working on that only. | 2) Will have a discussion on reviewing gantt chart. | 2) Learning swing basics. | 2) Still researching.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
vamsy | 1) worked with mani on Decelration code. | 1)Integration of code | 1)Done with integration part | 1)Worked on presentaion for the workshop | 1) Worked on workshop
| 2)Integration of both the codes | 2)Working on integration of code. | 2)Work on workshop | 2)preparation for the workshop | 2)Prepare for the presentation
| 3)No Obstacles | 3)No obstacles. | 3)No Obstacles. | 3)No Obstacles | 3)No obstacles.
Teja | Researched on displacement of cars | Continued research on the displacement module | Worked on velocity algorithm | Researched on various components required for velocity algorithm | Reviwed the displacement module
| started research on other modules | Started working on acceleration and velocity | Continued working on the same. | Continued the research | Researched on integration on velocity and displacement
| No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now | No Blockers
Ram Naveen | Met with the modeule artner and discussed about the classes that has to be implementeed. | Listed out the methods that are need to be done in class. | Devloped code for the direction on seeing various scenarios. | Worked on logic for percentage distribution. | Got an issue with the percentage distribution.
| Created clases that need to be done. | Had an interaction with roopananda about the current scenario. | Made some changes in code inorder to fit into project. | Prepared a protoype code for percentage distribution. | Discussed with the team about the percentage distribution Issue.
| No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now | Had an issue on direction change
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 2
Daily Stand-up Meeting Report
Week: January 15 - January 21
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Start initial version of the application | 1) Start initial version of the application | 1) Worked through Iteration plan | 1) Worked on simulation panel | 1) Worked through Iteration plan
| 2) Start initial version of the application | 2) Worked on simulation panel | 2) Worked on simulation panel | 2) Worked through Iteration plan | 2) Worked on simulation panel
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1) Researched on loading default values. | 1) Research on loading default values | 1) Researched on issue tracking system. | 1) Researched on issue tracking system. | 1) Worked on issue tracking system.
| 2)Research on loading default values. | 2) Research on issue tracking system. | 2) Research on issue tracking system. | 2) Came up with an idea and explained team | 2) Research on loading default values.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Rupanandha | Worked on charting the UML | Continued working on ULM | Continued working on ULM | Compled the UML and started coding | Designed the calsses for the app development
| No Blockers | No Blocker | No Blocker | No Blockers | No Blockers
Mani | 1) Started working on car accleration | 1) Worked on car accleration | 1) Finised working on car accleration. | 1) Worked on car deceleration | 1) Worked on car deceleration
| 2) Will be working on this module only. | 2) Will be working on this module only. | 2) Will be working on car deceleration. | 2) Will be working on car deceleration. | 2) Will be finishing car deceleration code.
| 3) No obsacles. | 3) No obsacles. | 3) No obsacles. | 3) No obsacles. | 3) No obsacles.
vamsy | First day of class after vacation. | Gone through the requirements document. | Assigned roles and work to be done to team members. | Gone through the swing tutorials. | Gone through the swing tutorials.
| Go through the requirements document. | Assign work to all team members. | Started working on swing. | Working on swing. | Worked with some examples.
| No obstacles. | No obstacles. | No obstacles. | No obstacles. | No obstacles.
Teja | Reviewed all the components required for modules assigned to me | Started research about all the components | Researched about all the speed related components | Continued studying about speed components | Researched about all the speed related components
| Planned how to proceed with the work | Research on the components | Have understood how to begin the coding module associated with velocity and displacement | Have understood how to begin the coding module associated with velocity and displacement | Have understood how to begin the coding module associated with velocity and displacement
| No obstacles | No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now
Ram Naveen | Created UML diagram for the project. | Distributed modules among the team | Gone through the existing system | Worked on percentage with some regular calculatins. | Discussed some useful stuff with the group.
| Assigned work accordig to the tasks. | Done some reasearch on my module. | Had some clear Idea about hat to do on project. | Had some research on direction change | Developed code on percentage distribution.
| No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 1
Daily Stand-up Meeting Report
Week: January 09 - January 14
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1) Gone through reading the requirements document. | 1) Review the requirement document | 1) Prepared Iteration plan presentation which was presented on Wednesday | 1) Prepared Iteration plan presentation which was presented on Wednesday | 1) Preparing the team for upcoming development of application
| 2) Review the requirement document | 2) Prepared Iteration plan presentation which was presented on Wednesday | 2) Prepared Iteration plan presentation which was presented on Wednesday | 2) Preparing the team for upcoming development of application | 2) Preparing the team for upcoming development of application
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Ashwini | 1) Client approved the project at the end of GDP - I. Vacation and first day | 1) Gone through reading the requirements document. | 1) Gone through reading the requirements document. | 1)Gone through reading the requirements document. | 1) Worked on loading default values.
| 2)Gone through reading the requirements document. | 2)Gone through reading the requirements document. | 2) Gone through reading the requirements document. | 2) Started working on loading the default values. | 2) Doing research on loading the default values.
| 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now | 3) No obstacles till now
Rupanandha | Prepared the Iteration plan | Prepared a mile stone document | Prepared for the presentation | Discussed with member abou the iteration plan | Worked on documenting the Sequence digaram
| No Blockers | No Blockers | No Blockers | Statt analyzing the module assigned to me | No Blockers
No blockers
Mani | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation.
vamsy | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation.
Teja | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation. | I am on vacation.
Ram Naveen | 1. First day of the class after vacation. | 1. Discussed about comments made by the proffesor for final submission. | 1. Alalyzed the requirements document. | 1. Presented iteration plan to the client. | With the modfied iteration plan submitted to the client.
| 2. Met each other and had a friendly conersation. | 2. Gone through the requirements again. | 2. Made an Idea about preparing iteration plan. | 2. Made changes on iteration plan. | Discussed about the projet progress with the team.
| No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now | No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?