## Week 5.
Daily Stand-up Meeting Report
Week: October 2 - October 8
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | 1)Check rules for signal | 1) Confirmed for 3 lights inspite of 4(protected light) | 1) Read some research papers on Traffic simulations | 1)Worked on drag and drop feature | Working on python technology
| 2) Working on the requirement of number of lights | 2) Working on the requirement of number of lights | 2)Work on created drag and drop feature | 2) Comparing Swing and other similar technologies | 2) Checking python for drag and drop
| 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet | 3) No obstacles yet
Ashwini | 1)Worked on the test case documentation little | 1)Worked on the test case document middle level | 1)Worked on the test case documentation at to finish | 1)Worked and completed test case documentation | 1)Worked and complete the installation documentation
| 2)Working on test case documentation | 2)Working on the test case documentation | 2)Working on test case documentation | 2)Working on the installation documentation and test suite | 2)Working on the test suite document
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Working use case documenting | 1)Working on use case documentation | 1) Working on Usecase documentation | 1) Working on Usecase documentation | 1) Working on Usecase documentation
| 2)Researching Swing | 2) Researching on SWING | 2)Researching through HTML 5 | 2)Researching through HTML 5 | 2)Researching through HTML 5
| 3)No blockers | 3)No blockers | 3)No Blockers | 3)No Blockers | 3)No Blockers
Mani | 1)Started working on requirement document. | 1)completed about 80% of document along with sahil. | 1)completed requirement document. | 1)started working on presentation. | 1)Completed about 50% of ppt.
| 2)Should complete the requirements document about 70 %. | 2)should finish the requirement document. | 2)Start working on midterm presentation. | 2)complete about 50 % of ppt. | 2)Finsh midterm presentation.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Discussed the format need to be followed in the Documentation | 1)Working on the Issues Management Documentation | 1)Working on the Issues Management Documentation | 1)Completed the Issues Management Document | 1)Done with the Documentation and reserching regarding the drawbacks of using HTML5 for the UI
| 2)Working on the Issues Managemnet Document | 2)Working on the Issues Management Documentation | 2)Working on the Issues Management Documentation | 2)Gone through the Document inorder to finalise and submittion | 2)Prepare for the Presentation
| 3)No Issues till now | 3)No Obstacles | 3)No Obstacles | 3)No Obstacles | 3)Need to Submit the Documents before Deadline
Teja | 1)Looking forward to sort out all the possible complications that might arise | 1) Trying to sort the issues related to different traffic models | 1)Resolved few issues that I came across while doing work | 1)Sample prototype in progress | 1)Tried sample prototype using html5 and javascript.
| 2) Checking for loop holes in the design | 2) Working on the basic traffic system Issues that might increase complexity | 2)Implementing different tools so that it will help me keep a record all issues | 2) Implemented few techniques that I have learned | 2) Compared the work accomplished using two different technologies.
| 3)Got a clarity on which technology to use | 3) No obstacles as yet | 3)No major complications yet | 3)Discussed with the team regarding technology selection | 3) Looking forward to meeting with the client.
Ram Naveen | 1. I took the responsibility of preparing testplan and prototypes | 1. Collected a sample document on test plan | 1. Created a prototype based on project | 1. Disccussed test plans to have more ideas | 1. Presented both the documents with the team
| 2. Looked on IEEE standard document to get a basic idea | 2. Reasched on various ways to test the requiremnts | 2. Had some doubts regarding project | 2. Documented these test plans which we have discussed | 2. Had approval from the team for those requriments
| 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 4
Daily Stand-up Meeting Report
Week: September 26 - September 30
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read 2 way rules | Read 4- way rules | Read 4- way rules | Read technologies stack | Read technologies stack
| Read 4- way rules | Read 4- way rules | Read 4- way rules | Read technologies stack | Read technologies stack
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Worked on the look and feel of the project | 1) Checked few cases for testing the project | 1)Checked more cases for testing | 1)Worked on some of the testing tools | 1)Completed test cases
| 2) Checking the test cases for the project | 2) Researching more cases for testing | 2)Working on the testing tools suitable for testing | 2)Researching test cases | 2)Working on test case documentation
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents | 1) Preparing the documents
| 2)Updating the requirement doc | 2)Reading through the depending docs | 2)Reading through the depending docs | 2)Reading through the depending docs | 2)Reading through the depending docs
| 3)No Blocker | 3)No Blocker | 3)No Blocker | 3)No Blocker | 3)No Blocker
Mani | 1)Known how to requirements document. | 1)Gone through some requirements | 1)Found the key requirements and started documenting. | 1)Started doing research on swing. | 1)Countined doing research on swing.
| 2)Should go through overview of requirements | 2)Should find the key requirements and start documenting. | 2) Should do some research on swing. | 2)should continue research on swing. | 2) should continue documenting requirements.
| 3)No issues till now. | 3)No issues till now. | 3) No issues till now. | 3)No issues till now | 3)No issues till now.
vamsy | 1)Researched all kind of issues that might occur in future. | 1)Gone through the requiremnts and found an issue. | 1)working on the tools that helps us keep track of all the issues. | 1)still working on tools. | 1)Updated some of the Issues in the Issues document.
| 2)Go through all the requiremnts in order to find the issues. | 2)Need to disscuss with the team members regarding the issue. | 2)resolved the issue that I came across last week | 2)need to finalize the tools for the issues record maintenance. | 2)Make some changes to the Issues document.
| 3)No obstacles yet | 3)Issue need to be resolved. | 3)no issues | 3)no issues | 3)No Issues.
Teja | Learning technolgies for prototype implementation | Worked on sample functions in swing and javascript | Practicing technolgies | Practicing the technologies | Continuing the practice of the technologies
| Focus is on technolgies and implementation | Practicing the technologies | Gone through swing API | Focus Shifted to html5 and javascript | Focus is on html5 and javascript
| No major complications yet | No major complications yet | No major issues | The issue of Technology selection is yet to be resolved | The issue of Technology selection is yet to be resolved
Ram Naveen | 1) Exploring various testing tools to test the project | 1) Selecting some software tools wich would useful to project | 1)Working on testing tools and forwarding to group members | 1)Working on testing tools and forwarding to group members | 1) Working on Creating test plans
| 2) Watching videos about swing to get basuc idea | 2)Looking forward to discuss among team members about tools in next meeting | 2) Learning on swing through tutorials | 2)2) Learning on swing through tutorials | 2) Had some doubts on HTML5
| 3. No obstacles till now | 3) No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)Need to talk in next meeting
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 3
Daily Stand-up Meeting Report
Week: September 19 - September 23
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read Reoundabout rules | Read Reoundabout rules | Read Signals rules | Read Signals rules | Read 2 way rules
| Read Reoundabout rules | Read Signals rules | Read Signals rules | Read 2 way rules | Read 2 way rules
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Learned swing until containers | 1) Worked on sample application | 1)Worked on sample application | 1)Worked on sample application | 1)Worked on sample application
| 2) Started working on sample application in swing | 2)Working on sample application in swing | 2)Working on sample application in HTML5 | 2)Working on sample application in HTML5 | 2)Working on look and feel of the project
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck | 1)Researching through the tech satck
| 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers
Mani | 1)Attended client meeting and discussed about requirements. | 1) Went through some parts of traffic modelling system. | 1)Got to know how the system works. | 1) Gone through some of the prototypes. | 1)Got some finalized prototypes.
| 2)Need to go through some previous traffic modelling system. | 2) Should go through this modellling system in depth. | 2)Should see some prototypes of the traffic modelling system. | 2) Should finalize some prototypes amound which I reviewd. | 2)Should know how to write requirements document.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Attended the Client Meeting and got some of the Issues resolved | 1)Documented the changes that are made Client Requirements Document. | 1)Gone through the Tools for the implementation. | 1)Worked on the Prototypes | 1)Workedon the Prototypes
| 2)Should document the changes made to the Client Requirements Document. | 2)Should go through the possible tools for the implementation. | 2)Should study the Tools for the implementation. | 2)Should work on the Prototypes | 2.)Attend the Client Meeting.
| 3)No Issues | 3)No Issues. | 3)No Issues | 3)No Issues. | 3)No Issues.
Teja | Analyzed the inputs for the project in a clear way | Trying to decide what inputs are unnecessary | Analyzing various techniques useful for the project | Trying to analyze different technologies | Had gathered useful information from the client
| Studying through the client requirements | Studying through the client requirements | Documenting requirements | Trying to learn the technologies useful for building the project | Learning the technologies
| No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet
Ram Naveen | Decided to do some sample prototypes | 1. Working on sample prototypes | 1.Shared sample prototypes among team. | 1. Working on test tools which are useful for project | 1.Had a proposal about HTML5
| 2. Discusssed among team. | 2. Developed some sample prottypes | 2. Disussed on testing tools to use. | 2. Gone through various tes cases. | Sheduled client meeting to discuss with client
| 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 2
Daily Stand-up Meeting Report
Week: September 12 - September 16
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read continuous event simulation sys | Read Coffee Script | Go through Missouri laws | Read github | Read github
| Read Coffee Script | Go through Missouri laws | Read github | Read github | Read github
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Started learning Swing | 1)Installed the swing on my laptop | 1)Learned swing until event handling | 1)Learned swing until event listeners | 1)Learned swing until layouts
| 2)Installing the swing on my laptop | 2)`Learning swing until event handling | 2)Learning swing until event listeners | 2)Learning swing until layouts | 2)Learning swing until containers
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding | 1) Connecting the dots based on the understanding
| 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers | 2) No Blockers
Mani | 1) Got some idea of the project from first client meeting. | 1)Got some knowledge on event simlation. | 1)Got to known somemore about Event Simulation. | 1)Started working on discrete event simulation. | 1)Got some more knowledge on discrete event simulation.
| 2)Should study on event simulation. | 2)should get some more knowledge on event simulation. | 2)Should start working on discrete event simulation. | 2)should improve my knowledge on discrete event simulation. | 2)Should attend client meeting.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Got to know the requirements of the client. | 1)Gone through the requiremts document. | 1)Done some research on the requirements. | 1)Discrete Event Simulation | 1)Got some more knowledge on discrete event simulation.
| 2)Should go through the client requiremnts. | 2)Should do some reserach whether all the requiremnets are possible for implementation. | 2)Discrete Event Simulation | 2)Should get some more knowledge on Discrete Event Simulation | 2)Client meeting
| 3)Should get to know all the possible cases from the Client Requirements. | 3)Should get to know all the possible cases from the Client Requirements. | 3)Should get to know all the possible cases from the Client Requirements. | 3)No issues | 3)No Issues
Teja | Trying to analyze the project requirements | Analyzing inputs for the project | Documenting all the inputs required for the project | Analyzing the design the of the project | Researching about simulation
| Researching on swing technology | Studying the implementation of existing system | Studying the implementation of existing systems | Checking whether the existing techniques are useful for the project or not. | Learning the techniques useful for simulation
| No obstacles yet | No obstacles yet | No obstacles yet | No obstacles yet. | No obstacles yet
Ram Naveen | 1. Have searched about existing system | 1. Proffesor sugested on swing and java | 1. Every one are new to the swing software | 1. Working on swing tutorial | 1. Looking some videos on swing tutorial
| 2. No obstacles yet. | 2, Had a convesation on technology | 2. Decided to work on swing | 2. Learning swing tutorial | 2. Looking on projects which are based on swing
| 3. No obstacles till now | 3. No obstacles yet | 3. No obstacles till now | 3. No obstacles till now | 3. No obstacles till now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?

## Week 1
Daily Stand-up Meeting Report
Week: September 5 - September 9
Project Name: Traffic Modeling System
Team Name: Ekathra
| Monday | Tuesday | Wednesday | Thursday | Friday
Sahil | Read about Discrete Event Simualtion | Read some research papers | Read continuous event simulation sys | Read about Requirement gathering documents | Go through the existing system
| Read some research papers | Read continuous event simulation sys | Read about Requirement gathering documents | Go through the existing system | Read continuous event simulation sys
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Ashwini | 1)Read the articles regaring the project | 1) Got to now a little about the project | 1)Got the clear idea of the project | 1)Worked on checking the UI | 1)Checked the UI of drop down of different sites
| 2)Understanding the project and client expectations | 2)Understanding the project and client expectations | 2)Started checking the UI of exsisting traffic websites | 2)Checking the UI of drop down of exsisting sites | 2)Checking the UI of button of various websites
| 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now | 3)No obstacles till now
Rupanandha | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project | 1) Reading through the project
| 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems | 2)Reading through the existing systems
| 3) No Blockers | 3) No Blockers | 3) No Blockers | 3) No Blockers | 3) No Blockers
Mani | 1)Got to know the project and roles. | 1)known about the roles | 1)Just known about traffic systems and their importance. | 1)Got a very breif idea about traffic systems. | 1)Gone through some traffic rules.
| 2) yet to decide roles. | 2) Trying to understand the project. | 2)Trying to know more about traffic systems. | 2)Studied some traffic rules. | 2)should attend a meeting with the client.
| 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now. | 3)No issues till now.
vamsy | 1)Assigned the roles to all the team members | 1)Got to know about my role. | 1)Studied some of the presently available Traffic Simulation Softwares | 1)Done some research regarding the requrements for the project. | 1)Wrote down some of the key constraints.
| 2)Got to know about my role. | 2)Stould study some of the presently available Traffic Simulation Softwares | 2)Should do some research regarding the requrements for the project. | 2)Should write down the key Constraints that need to be considered. | 2)Attend the Client meeting Should ge a clear understanding of the project requirements.
| 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)Should get a clear view about the requirements. | 3)No obstacles.
Teja | Got to know about my role. | Trying to analyze the requirements of project | Reading the implementations of existing systems | Reading the implementations of existing sytems | Learning through existing systems
| Researched on exisiting systems | Researching technologies for implementation | Learning the implementation techniques | Learning implementation techniques | Jotted down all the important techniques from various sources
| No obstacles yet | No major obstacles yet | No major complications yet | No obstacles upto now | No obstacles upto now
Ram Naveen | 1. Based on client meeting we have researched about project | 1. Had some research on existing system | 1. Professor said about project | 1. Shared our views | 1. We had a client meeting.
| 2. Discussing on requiirements | 2. Decided to do some more work on exising system | 2. We searched on various site about project | 2. Had some research on traffic rules | 2. Came to know about the project
| 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now | 3. No obstacles upto now
Note:
1. What did I accomplish yesterday? 2.What will I do today? 3.What obstacles are impeding my progress?